## create a wbs for this project w
Module | Submodule | Task ID | Task Description | Status | Due Date
Project Setup | Environment | 1.1 | Project environment setup (Git, hosting, database schema) | Not Started | 2025-08-07
Authentication | API | 1.2 | Build Login & JWT Session Management API | Not Started | 2025-08-07
|  | 1.3 | Implement 2FA Email/OTP (generate, send, verify) API | Not Started | 2025-08-08
| Frontend | 1.4 | React Login UI + 2FA screens + form validation | Not Started | 2025-08-11
| API | 1.5 | Forgot/Reset Password flow API (send link, token validation) | Not Started | 2025-08-11
| Frontend | 1.6 | Forgot/Reset Password UI + error handling | Not Started | 2025-08-12
|  | 1.7 | Unit testing & bug fixes for authentication flow | Not Started | 2025-08-13
Advisor | Dashboard | 2.1 | Advisor Dashboard UI (Greeting, Metrics, Charts) | Not Started | 2025-08-14
| Client List | 2.2 | Client Table View UI (search, sort, pagination) | Not Started | 2025-08-18
|  | 2.3 | API: Clients CRUD + search/sort/filter endpoints | Not Started | 2025-08-18
| Client Profile | 2.4 | Add/Edit Client modal with validation | Not Started | 2025-08-19
|  | 2.5 | Email Modal with Rich Text Editor (send emails to clients) | Not Started | 2025-08-20
|  | 2.6 | Client Summary View + Document Upload UI | Not Started | 2025-08-21
|  | 2.7 | File Upload API + secure storage + role-based access | Not Started | 2025-08-22
Admin | Settings | 3.1 | Admin Settings UI (2FA, password policy, theme, fonts) | Not Started | 2025-08-25
|  | 3.2 | API: Admin settings endpoints (update global configs) | Not Started | 2025-08-25
| Content | 3.3 | Fact Finder Configurator (Dynamic Question Builder UI) | Not Started | 2025-08-26
Client | Fact Finder | 4.1 | Client Dashboard UI + Sidebar Navigation | Not Started | 2025-08-27
|  | 4.2 | Fact Finder Multi-Step Form (Personal Info, Assets, etc.) | Not Started | 2025-08-27
|  | 4.3 | API: Auto-Save logic + continue/back navigation | Not Started | 2025-08-27
|  | 4.4 | Load dynamic questions in client view (Investor Profile logic) | Not Started | 2025-08-28
Finalization | Testing | 5.1 | Final testing of all modules & bug fixes | Not Started | 2025-08-28
| Deployment | 5.2 | Final deployment to production environment | Not Started | 2025-08-29